## Sheet1
| Fall 2021 | Phase 1 |  |  | Phase 2 |  | Phase 3 | [5 empty] | Spring 2022 | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4 |  |  | Phase 5
|  | Milestone 1 |  |  | Milestone 2 |  | Milestone 3 |  |  |  |  | Retrospective
|  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15
|  | 9/17/21-9/21/21 | 9/24/21-9/29/21 | 9/30/21-10/05/21 | 10/07/21-10/14/21 | 10/22/21-10/27/21 | 10/29/21-11/03/21 | 11/05/21-11/10/21 | 11/12/21-11/17/21 | 11/19/21-11/24/21 | 11/26/21-12/01/21 | 12/03/21-12/08/21 |  | 1/21/22-1/26/22 | 1/28/22-2/2/22 | 2/4/22-2/9/22 | 2/11/22-2/16/22 | 2/18/22-2/23/22 | 2/25/22-3/2/22 | 3/4/22-3/9/22 | 3/11/22-3/16/22 | 3/18/22-3/23/22 | 3/25/22-3/30/22 | 4/1/22-4/6/22 | 4/8/22-4/13/22 | 4/15/22-4/20/22 | 4/22/22-4/27/22 | 2/29/22-5/4/22
Spring Break 3/28/22-4/1/22 |  | Project Propsal | Tech Spec | HL Design | Project Plan | Network Diagram | Low Level Design | Low Level Design | UM | Logging | Milestone 1 Revisions | Retrospective Review |  | Cloud Server Setup | Registration | User Management | Creating a node | Changing contents | Changing tag | Setting node public | Rating | Searching | Copying a node | Pasting a node | Error Handling | Data Store Access | Documentation | Prepare for final deliverable
Finals 5/9/22-5/14/22 |  | Milestone 1 Sprint 0: BRD; Milestone 1 Sprint 1: Site Map; Milestone 2 Sprint 3: Test Plan; Milestone 2 Sprint 4: Milestone 1 revisions; Milestone 3 Sprint 9: Milestone 2 Revisions |  |  | Network Communication | Login | User access control |  |  |  | Privatizing node | Usage analysis Dashboard
[14 empty] | Logging | Logout
Deploy on Thursdays
Max Team Capacity-
Med Team Capacity-
Min Team Capacity-
Avg Expected Team Capacity-
Viet
10
7
5
Matthew
Jessie
12
9
6
Pammy