## Sheet1
| Fall 2021 Project Roadmap | Phase 2 |  | Phase 3 |  |  | Retrospective
|  | Milestone 2 |  | Milestone 3 |  |  | 12/09/21-12/17/22
|  | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Retrospective Review
|  | 10/07/21-10/14/21 | 10/22/21-10/27/21 | 10/29/21-11/10/21 | 11/12/21-11/24/21 | 11/26/21-12/08/21 | Finals Review
|  | Project Plan | Project Plan | Low Level Design | UM | Logging
|  | Test Plan | Test Plan | BRD Revisions | Project Plan Revisions | Retrospective Prep
|  | Default Items | Network Diagram | Tech Spec Revisions | Test Plan Revsions | Default Items
|  |  | Default Items | Site Map Revisions | Network Diagram Revisions
|  |  |  | HL Design Revisions | Default Items
Default Items
Start: 1/21/22 | Spring 2022 Project Roadmap | Phase 1 | Phase 2 | Phase 3 | Phase 4
End: 5/4/22 |  | 1/21/22-2/16/22 | 2/18/22-3/16/22 | 3/18/22-4/13/22 | 4/15/22-5/4/22
|  | Datastore Access | Login/Logout (Authentication and Logout) | Copying a node | Changing parent of node
|  | User Access Control (Authorization) | Registration | Changing contents of nodes
|  | User Management (includes Account deletion by normal users and system admins, Account recovery | Creating a node | Usage Analysis Dashboard
|  |  | Deleting a node | Pasting a node
|  |  | Setting nodes private/public | Changing tags of nodes
|  |  | Searching | Rating