## Sheet1
|  | Spring 2022 | Phase 1 | [5 empty] | Phase 2 | [5 empty] | Phase 3 | [5 empty] | Phase 4 | [7 empty] | Expected Low Work Times
|  |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Sprint 7 |  |  | Sprint 8 |  |  |  |  | Spring Break 3/28/22-4/1/22
|  |  | Assignee | 1/21/22-2/2/22 | Estimate | Assignee | 2/4/22-2/16/22 | Estimate | Assignee | 2/18/22-3/2/22 | Estimate | Assignee | 3/4/22-3/16/22 | Estimate | Assignee | 3/18/22-3/30/22 | Estimate | Assignee | 4/1/22-4/13/22 | Estimate | Assignee | 4/15/22-4/27/22 | Estimate | Assignee | 4/29/22-5/4/22 | Estimate |  |  | Finals 5/9/22-5/14/22
|  | Work Items | J | Database Setup | 16 | P | Datastore Access (Network Communication, Error handling, Testing, Documentation) | 8 | V | Login/Logout (authentication and logout) | 14 | P | Deleting a node | 19 | P | Copying a node | 20 | P | Pasting a node | 20 | P | Changing parent of node | 23 |  | Final Deployment Setup | 25
|  |  | P | Datastore Access (Analyzation, Access Requirements, SQL), Database Setup | 20 | V | User Access Control (authorization) | 14 | J | Registration (User Privacy) | 14 | V | Setting nodes private/public | 13 | V | Changing contents of nodes | 11 | V | Changing tags of nodes | 11 |  | Final Testing/Documentation | 25 |  | Final Deployment | 25
|  |  | V | Cloud Setup, Database Setup | 16 | J | User Management (Account deletion by both normal users and system admin, Account recovery) | 19 |  | Account Recovery |  | J | Searching | 14 | J | Usage Analysis Dashboard | 14 | J | Usage Analysis Dashboard | 9 | M | Deployment on Thursdays | 4 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 |  |  | Default Items | 16
|  |  | M | Deployment on Thursdays | 4 | M | Logging/Archiving | 10 | P | Creating a node | 19 | M | Deployment on Thursdays | 4 | M | Deployment on Thursdays | 4 | M | Rating | 11 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 |  |  | Deployment on Thursdays | 4
|  |  | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Deployment on Thursdays | 4 | M | Deployment on Thursdays | 4 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Deployment on Thursdays | 4 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Sprint retrospective-half way and/or last day of sprint | 2 |  |  | Backlog Grooming/Half way and Thursdays between sprints | 3
|  |  | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Backlog Grooming/Half way and Thursdays between sprints | 3 | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 |  |  | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4
|  |  | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Sprint planning-Thurdays between sprints and possibly first/last day of current/next sprint | 4 | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | [5 empty] | Sprint retrospective-half way and/or last day of sprint | 2
|  |  | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Sprint retrospective-half way and/or last day of sprint | 2 | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | M | Sprint retrospective-half way and/or last day of sprint | 2 | [8 empty] | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3
[6 empty] | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | M | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3 | [7 empty] | Client feedback/demo-Office hours days (Thurdays and Saturdays) | 3
|  | Tasks |  | DB: Purpose for each database | 2 |  | DA: Network Communication | 2 |  | Login/Logout: Insert/Queries | 2 |  | Delete: Insert/Queries | 2 |  | Copy: Insert/Queries | 2 |  | Paste: Insert/Queries | 2 |  | Parent: Insert/Queries | 2 |  | Final Deployment Setup | 25
|  |  |  | DB: Find and organize information that we will be needing | 6 |  | DA: Error Handling | 2 |  | Login/Logout: UI | 4 |  | Delete: UI | 7 |  | Copy: UI | 8 |  | Paste: UI | 8 |  | Parent: UI | 10 |  | Final Deployment | 25
|  |  |  | DB: Determine classes/tables | 6 |  | DA:Testing | 3 |  | Login/Logout: Network Communication | 2 |  | Delete: Network Communication | 2 |  | Copy: Network Communication | 2 |  | Paste: Network Communication | 2 |  | Parent: Network Communication | 2 |  | Deployment | 4
|  |  |  | DB: UML and Relation Scheme Diagraming | 6 |  | DA: Documentation | 1 |  | Login/Logout: Error Handling | 2 |  | Delete: Error Handling | 2 |  | Copy: Error Handling | 2 |  | Paste: Error Handling | 2 |  | Parent: Error Handling | 2 |  | Backlog Grooming | 3
|  |  |  | DB: Refining | 6 |  | UAC: Insert/Queries | 2 |  | Login/Logout: Testing | 3 |  | Delete: Testing | 5 |  | Copy: Testing | 5 |  | Paste: Testing | 5 |  | Parent: Testing | 6 |  | Sprint Planning | 4 |  |  | Costs | 0
|  |  |  | DB: SQL | 6 |  | UAC: UI | 4 |  | Login/Logout: Documentation | 1 |  | Delete: Documentation | 1 |  | Copy: Documentation | 1 |  | Paste: Documentation | 1 |  | Parent: Documentation | 1 |  | Sprint Retrospective | 2 |  |  | Budget | 100
|  |  |  | DB: Testing | 3 |  | UAC: Network Communication | 2 |  | Registration: Insert/Queries | 2 |  | Private/Public: Insert/Queries | 2 |  | Contents: Insert/Queries | 2 |  | Tags: Insert/Queries | 2 |  | Final Testing/Documentation | 25 |  | Client Feedback/Demo | 3 |  |  | Estimates are in hours
|  |  |  | DB: Documentation | 3 |  | UAC: Error Handling | 2 |  | Registration: UI | 4 |  | Private/Public: UI | 3 |  | Contents: UI | 2 |  | Tags: UI | 2 |  | Deployment | 4
|  |  |  | DA: Analyzation | 3 |  | UAC: Testing | 3 |  | Registration: Network Communication | 2 |  | Private/Public: Network Communication | 2 |  | Contents: Network Communication | 2 |  | Tags: Network Communication | 2 |  | Backlog Grooming | 3
|  |  |  | DA: Access Requirements | 2 |  | UAC: Documentation | 1 |  | Registration: Error Handling | 2 |  | Private/Public: Error Handling | 2 |  | Contents: Error Handling | 2 |  | Tags: Error Handling | 2 |  | Sprint Planning | 4 | [5 empty] | Week | Sprint
|  |  |  | DA: Inserts/Queries | 3 |  | UM: Insert/Queries | 2 |  | Registration: Testing | 3 |  | Private/Public: Testing | 3 |  | Contents: Testing | 2 |  | Tags: Testing | 2 |  | Sprint Retrospective | 2 | [5 empty] | Max Team Capacity-42 | Max Team Capacity-84
|  |  |  | Cloud: Setup | 3 |  | UM: UI | 7 |  | Registration: Documentation | 1 |  | Private/Public: Documentation | 1 |  | Contents: Documentation | 1 |  | Tags: Documentation | 1 |  | Client Feedback/Demo | 3 | [5 empty] | Med Team Capacity-35 | Med Team Capacity-70
|  |  |  | Cloud:Testing | 3 |  | UM: Network Communication | 2 |  | Create: Insert/Queries | 2 |  | Searching: Insert/Queries | 2 |  | UAD: Insert/Queries | 2 |  | UAD: Error Handling | 2 | [8 empty] | Min Team Capacity-27 | Min Team Capacity-54
|  |  |  | Deployment | 4 |  | UM: Error Handling | 2 |  | Create: UI | 7 |  | Searching: UI | 4 |  | UAD: UI | 10 |  | UAD: Testing | 6 | [8 empty] | Avg Expected Team Capacity-32 | Avg Expected Team Capacity-64
|  |  |  | Backlog Grooming | 3 |  | UM: Testing | 5 |  | Create: Network Communication | 2 |  | Searching: Network Communication | 2 |  | UAD: Network Communication | 2 |  | UAD: Documentation | 1 | [9 empty] | 512
|  |  |  | Sprint Planning | 4 |  | UM: Documentation | 1 |  | Create: Error Handling | 2 |  | Searching: Error Handling | 2 |  | Deployment | 4 |  | Rating: Insert/Queries | 2 | [8 empty] | Jessie (J) | 16
|  |  |  | Sprint Retrospective | 2 |  | Logging: Insert/Queries | 3 |  | Create: Testing | 5 |  | Searching: Testing | 3 |  | Backlog Grooming | 3 |  | Rating: UI | 2 | [8 empty] | Matthew (M) | 16
|  |  |  | Client Feedback/Demo | 3 |  | Logging: Network Communication | 2 |  | Create: Documentation | 1 |  | Searching: Documentation | 1 |  | Sprint Planning | 4 |  | Rating: Network Communication | 2 | [8 empty] | Pammy (P) | 22
[7 empty] | Logging: Error Handling | 2 |  | Deployment | 4 |  | Deployment | 4 |  | Sprint Retrospective | 2 |  | Rating: Error Handling | 2 | [8 empty] | Viet (V) | 16
[7 empty] | Logging: Testing | 2 |  | Backlog Grooming | 3 |  | Backlog Grooming | 3 |  | Client Feedback/Demo | 3 |  | Rating: Testing | 2
[7 empty] | Logging: Documentation | 1 |  | Sprint Planning | 4 |  | Sprint Planning | 4 |  |  |  |  | Rating: Documentation | 1
[7 empty] | Deployment | 4 |  | Sprint Retrospective | 2 |  | Sprint Retrospective | 2 |  |  |  |  | Deployment | 4
[7 empty] | Backlog Grooming | 3 |  | Client Feedback/Demo | 3 |  | Client Feedback/Demo | 3 |  |  |  |  | Backlog Grooming | 3
[7 empty] | Sprint Planning | 4 | [10 empty] | Sprint Planning | 4
[7 empty] | Sprint Retrospective | 2 | [10 empty] | Sprint Retrospective | 2
[7 empty] | Client Feedback/Demo | 3 | [10 empty] | Client Feedback/Demo | 3
Test Cases
|  | Time/Sprint |  |  | 68 |  |  | 67 |  |  | 63 |  |  | 62 |  |  | 61 |  |  | 67 |  |  | 64 |  |  | 66
Estimates | Work Items |  |  | Estimates (Hours) |  |  | Initial Breakdown
[8 empty] | Estimate |  |  | Estimate |  |  | Estimate |  |  | Estimate |  |  | Estimate |  |  | Estimate
| Database Setup |  |  | 38 |  |  | Purpose for each database | 2 |  | Find and organize information that we will be needing | 6 |  | Determine classes/tables | 6 |  | UML and Relation Scheme Diagraming | 6 |  | Refining | 6 |  | SQL | 6 |  | Testing | 3 | Documentation | 3
| Datastore Access |  |  | 16 |  |  | Analyzation | 3 |  | Access Requirements | 2 |  | Inserts/Queries | 3 |  |  |  |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| Cloud Setup |  |  | 6 |  |  | Setup | 3 | [16 empty] | Testing | 3
| User Access Control |  |  | 14 | [8 empty] | Insert/Queries | 2 |  | UI | 4 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| User Management |  |  | 19 | [8 empty] | Insert/Queries | 2 |  | UI | 7 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 5 | Documentation | 1
| Logging |  |  | 10 | [8 empty] | Insert/Queries | 3 |  |  |  |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 2 | Documentation | 1
| Login/Logout |  |  | 14 | [8 empty] | Insert/Queries | 2 |  | UI | 4 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| Registration |  |  | 14 | [8 empty] | Insert/Queries | 2 |  | UI | 4 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| Creating a node |  |  | 19 | [8 empty] | Insert/Queries | 2 |  | UI | 7 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 5 | Documentation | 1
| Deleting a node |  |  | 19 | [8 empty] | Insert/Queries | 2 |  | UI | 7 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 5 | Documentation | 1
| Setting nodes private/public |  |  | 13 | [8 empty] | Insert/Queries | 2 |  | UI | 3 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| Searching |  |  | 14 | [8 empty] | Insert/Queries | 2 |  | UI | 4 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 3 | Documentation | 1
| Copying a node |  |  | 20 | [8 empty] | Insert/Queries | 2 |  | UI | 8 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 5 | Documentation | 1
| Changing contents of nodes |  |  | 11 | [8 empty] | Insert/Queries | 2 |  | UI | 2 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 2 | Documentation | 1
| Usage Analysis Dashboard |  |  | 23 | [8 empty] | Insert/Queries | 2 |  | UI | 10 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 6 | Documentation | 1
| Pasting a node |  |  | 20 | [8 empty] | Insert/Queries | 2 |  | UI | 8 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 5 | Documentation | 1
| Changing tags of nodes |  |  | 11 | [8 empty] | Insert/Queries | 2 |  | UI | 2 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 2 | Documentation | 1
| Rating |  |  | 11 | [8 empty] | Insert/Queries | 2 |  | UI | 2 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 2 | Documentation | 1
| Changing parent of node |  |  | 23 | [8 empty] | Insert/Queries | 2 |  | UI | 10 |  | Network Communication | 2 |  | Error Handling | 2 |  | Testing | 6 | Documentation | 1
| Final Testing/Documentation |  |  | 25 | [20 empty] | Testing
| Final Deployment Setup |  |  | 25 | [20 empty] | Testing
| Final Deployment |  |  | 25 | [20 empty] | Testing
| Default Items |  |  | 128
Total |  |  |  | 518